## Sheet1
ĐỌC BÁO GIÚP BẠN
| Project Lead: |  | Lê Minh Phúc
| Project Start Date: |  | 2017-09-22 | time axis 2017-09-18 to 2017-12-10
| Display Week: |  | 1 |  |  |  |  | 2017-09-18: Week 1; 2017-09-25: Week 2; 2017-10-02: Week 3; 2017-10-09: Week 4; 2017-10-16: Week 5; 2017-10-23: Week 6; 2017-10-30: Week 7; 2017-11-06: Week 8; 2017-11-13: Week 9; 2017-11-20: Week 10; 2017-11-27: Week 11; 2017-12-04: Week 12
[8 empty] | 2017-09-18 | [6 empty] | 2017-09-25 | [6 empty] | 2017-10-02 | [6 empty] | 2017-10-09 | [6 empty] | 2017-10-16 | [6 empty] | 2017-10-23 | [6 empty] | 2017-10-30 | [6 empty] | 2017-11-06 | [6 empty] | 2017-11-13 | [6 empty] | 2017-11-20 | [6 empty] | 2017-11-27 | [6 empty] | 2017-12-04
WBS | Task | Lead | Bắt đầu | Kết thúc | TG hoàn thành | % Hoàn Thành | Man-hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Sprint 1
1.1 | Phân tích yêu cầu khách hàng | Long | 2017-09-22 | 2017-10-05 | 14 | 100% | 7
1.2 | Một bản thiết kế website | Liêm | 2017-09-25 | 2017-10-04 | 10 | 100% | 5
1.3 | Tìm và làm các hình ảnh có chất lượng tốt | Kiệt | 2017-09-30 | 2017-10-04 | 5 | 100% | 4
| Bố trí nội dung sao cho hình ảnh và nội dung hài hòa với nhau | Kiệt | 2017-10-06 | 2017-10-15 | 10 | 0% | 7
| Học cách sử dụng animation | Kiệt | 2017-10-16 | 2017-10-19 | 4 | 0% | 3
1.4 | Sử dụng java swing | Kiệt | 2017-10-20 | 2017-10-29 | 10 | 0% | 7
| Sử dụng Esclipe để tương tác dễ | Kiệt | 2017-10-30 | 2017-11-02 | 4 | 0% | 3
1 | Thiết kế hệ thống
1.1 | Tạo một khung cho khách hàng nhập thông tin và yêu cầu và gửi thông tin yêu cầu tới NCC |  | 2017-09-25 | 2017-10-04 | 10 | 100% | 8
1.2 | Chuẩn bị bản thiết kế website trên di động |  | 2017-09-25 | 2017-10-04 | 10 | 100% | 8
1.3 | Nghiên cứu và bố trí hình ảnh |  | 2017-10-06 | 2017-10-15 | 10 | 0% | 7
| Điều chỉnh và sử dụng meta-view hợp lý |  | 2017-10-16 | 2017-10-19 | 4 | 0% | 3
| Áp dụng tối đa css |  | 2017-10-20 | 2017-11-18 | 30 | 0% | 7
1.4 | Một bản báo cáo phân công và đóng góp của thành viên |  | 2017-10-27 | 2017-11-15 | 20 | 0% | 3
2 | Thiết kế giao diện
2.1 | Vẽ wireframe |  | 2017-09-25 | 2017-10-01 | 7 | 100% | 10
2.2 | Thiết kế UI |  | 2017-09-25 | 2017-10-14 | 20 | 80% | 15
3.2.1 | Vẽ UI TĨnh |  | 2017-09-25 | 2017-10-01 | 7 | 80% | 5
3.2.2 | Thiết Kế Prototype |  | 2017-09-25 | 2017-10-24 | 30 | 80% | 22
4 | Phát triển phần mềm
4.1 | Viết mã nguồn |  | 2017-10-05 | 2017-12-03 | 60 | 0% | 42
4.2 | Unit Test |  | 2017-11-20 | 2017-12-03 | 14 | 0% | 10
5 | Kiểm thử
5.1 | Integration Test |  | 2017-10-20 | 2017-11-28 | 40 | 0% | 28
5.2 | System test |  | 2017-11-29 | 2017-12-01 | 3 | 0% | 3
6 | Release
6.1 | Triển khai giai đoạn 1 |  | 2017-10-09 | 2017-10-15 | 7 | 0% | 5
6.2 | Triển khai giai đoạn 2 |  | 2017-10-23 | 2017-10-29 | 7 | 0% | 5
6.3 | Triển khai giai đoạn 3 |  | 2017-11-06 | 2017-11-12 | 7 | 0% | 5
6.4 | Triển khai giai đoạn 4 |  | 2017-11-20 | 2017-11-26 | 7 | 0% | 5
6.5 | Bàn giao phần mềm |  | 2017-12-04 | 2017-12-10 | 7 | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on G7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.